## Sheet2
TASK NAME	DURATION	April		May					June					July

		29	30	1	2	3	4	6	7	8	9	10	11	13	14	15	16	17	18	20	21	22	23	24	25	27	28	29	30	31	1	3	4	5	6	7	8	10	11	12	13	14	15	17	18	19	20	21	22	24	25	26	27	28	29	1	2	3	4	5	6	8	9	10	11	12	13	15	16	17	18	19	20	22	23	24	25	26	27	29	30	31
		M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W	TH	F	S	M	T	W
Planning
Brainstorming on possible clients	3
Finalization of Project Plan
Drafting of WBS, Gantt Chart, & Pert Chart	3
Create request letters to the company	2
Letter Approval	1
Meeting the Client for the Approval	1
Discussion on different parts of Project paper	2
Finalization of the Work Breakdown Structure(WBS)	2
Finalization of the Gantt Chart	1
Finalization of the PERT Chart	1
Drafting and Revisions of Questions for Interview	1
Finalization of the Questionnaires	1
Conduct Final Interview	1

Analysis
Narrative description of As-Is Process	1
Analyze the data gathered from the interview	2
DFD of As-Is process	2
Narrative Flowchart of As-Is Process	2
Create a flowchart of As-Is process	3
Identify and list down the problems encountered in the existing processes	2
Create Ishikawa Diagram	2
Create Cost Benefit Analysis	2

Design
Identify the features of the proposed system	2
Create use-case diagram	3
Swimlane activity diagram	1
Sequence Diagram	4
UI design	4

Implementation
Narrative description for each feature of the proposed syatem	3
Use-case Diagram	3
Cost benefit Analysis	4